## Jira_Backlog
Issue ID | Issue Type | Title | Description | Priority | Story Points | Assigned To | Branch Name | Status
TR-1 | Epic | Setup Project Structure | Initialize Flask project and folder structure | High | 5 | Sukhvinder | feature/project-setup | To Do
TR-2 | Story | Integrate NLP Model | Load helsinki-nlp/opus-mt-en-hi model using transformers | High | 8 | Aman | feature/model-integration | To Do
TR-3 | Story | Create Translation API | Develop Flask route for handling translation POST request | High | 5 | Rohit | feature/api-translation | To Do
TR-4 | Task | Design Frontend UI | Create HTML form with input and output sections | Medium | 3 | Priya | feature/frontend-ui | To Do
TR-5 | Task | Input Validation | Handle empty input and error messages | Medium | 2 | Aman | feature/input-validation | To Do
TR-6 | Story | Deploy on Render | Configure Procfile and deploy app on Render | High | 5 | Sukhvinder | feature/deployment-render | To Do
TR-7 | Task | Create requirements.txt | Add flask, transformers, torch, gunicorn dependencies | Low | 2 | Rohit | chore/requirements-file | To Do
TR-8 | Task | Testing & Debugging | Test translation accuracy and fix bugs | Medium | 5 | Priya | feature/testing-debugging | To Do
TR-9 | Story | Improve UI Responsiveness | Make frontend responsive using CSS | Low | 3 | Aman | feature/ui-responsive | To Do
TR-10 | Task | Write Documentation | Prepare README and deployment steps | Low | 3 | Sukhvinder | docs/project-documentation | To Do